## Sheet1
WINTER GALA TASTING
EVENT CHECKLIST
Date of Event _____________________
Name or Theme of Event _________________________________
The Museum is reserved for the year; you do not need to reserve a room.
Museum staff are on site by 6:30 and this event starts at 6:30; because this a special
event you may need more time for setup and decorating, check with the Museum to see
if you can come in during the afternoon of the day of the event for up to an hour. Plan
on being cleaned up and out by 9 PM. (We pay for 2-1/2 hrs. If we use more time, we
have to pay for it.)
The cost for any champagnes or sparkling wines sampled by the organizing committee is
the responsibility of the committee members. If unopened bottles remain after the
tasting event, you can: a) keep them;b) sell them to other members; or c) sell them to
the society (the Board prefers a or b)
Prior to purchasing or ordering champagne or sparkling wine, the chairman should
discuss it with the society board president. The society board sets a budget for this
event. Also, be realistic about the number of bottles & attendees: for this event we
authorize 1 bottle per table of 8 people and typically the number of attendees is no
more than 72. When using 72 as the maximum number of attendees, use 66. We have
a document on the Anatomy of a Tasting Fee and a Winter Gala Fee Form included in this
packet.
Assign someone from the committee to attend the Enological Society Board meeting
the month prior to the event to present a budget and price (usually the Thursday
following the previous event). The Board must approve the tasting fee.
Tasting Notice information (prior to event) - include the following:
|  | * | Date
|  | * | Time
|  | * | Place
|  | * | What to bring, i.e., food
|  | * | Comments on dress if needed
|  | * | List of wines
|  | * | A short description of the event
|  | * | Number of attendees allowed
|  | * | Anything else that might be special to the event
Tasting notice information should be sent to Don Julien (donjulien@aol.com)
before the end of October or the 1st week of November. He will format for emailing to
members.
At the same time, send a picture of the wines or other “teaser” for our
for our Facebook page to Jan Lutz (lutzgal@gmail.com)
Prior to the event prepare a sheet with tasting notes for the wines being served and any
other materials you wish to provide.
Order a Banquet Permit online (lcb.wa.gov; $10; Do up to the day before
the event. We have a Liquor Licenses Fact Sheet included with this packet.
The permit is emailed you. Print 2 copies: one to post at the event & 1 to give
museum staff for their files.
Several weeks before the event, contact the Museum (888-6262) and ask for the person
in charge of event scheduling to confirm date & give contact info. The week of the event,
follow up with your museum contact re: setup & any other needs (We have a default
of up to 9 round tables w 8 chairs, 4 rect tables in lobby for food, 1 rect table for punch,
and 2 rect tables for the raffle items). You will need to let them know you need white
linens for all of the tables.
The week before the tasting, pick up supplies from storage. Restock any shortages and
keep receipts for reimbursement. Locker keys are held by Jim Hofmann (663-1630),
Bruce Campbell (663-1020) & Don Julien (881-4092)
Set-up room: (Museum staff does this; arrange any changes with your museum contact).
|  | * | Tables & chairs (9 Rounds with 8 chairs; table linens)
|  | * | Tables for food (4 rectangular; with table linens)
|  | * | Punch table (1 rectangular with table linen)
|  | * | Raffle tables (2 rectangular with table linens)
|  | * | PA System
If during set up additonal chairs or tables are necessary, they are available in a storage
closet on the north wall of the exhibit room.
Decorations (NOTE: lit candles are not allowed at Museum):
|  | * | Food tables
|  | * | Head table
|  | * | Guest tables
Food tables: (While the Society has supplies, you may need to replenish, keep receipts
for reimbursement)
|  | * | Table cloths (Request linens from the Museum)
|  | * | Paper plates (Usually use festive plates, check in storage or purchase)
|  | * | Flatware (Society has these; also blue plastic trays to hold flatware)
|  | * | Napkins (Usually have festive paper napkins, check in storage or purchase)
Guest tables:
|  | * | Table cloths (Request linens from the Museum)
|  | * | Water pitchers (Society has these, 1 per table)
|  | * | Dump containers (Society has these, 1 per table)
|  | * | Champagne glasses (request members bring their own)
|  | * | Programs with tasting notes, information about the wineries, rating
charts, or anything else to enhance the event
People at each table will select someone to to pour the champagne or sparkling wine
Arrange to take pictures at the event either by someone on your committee
or someone else. If possible, digital so can be sent to the web for posting.
Other Tasting Supplies:
|  | * | Will need punch bowl or 2 and ladles
Event management:
|  | * | From 6:30 to 7:15 social with a champagne pucnch
|  | * | The President conducts bit of business before intro of Event Chair
|  | * | Event Chair conducts short intro to event
|  | * | Periodically conduct raffle draws during the event
|  | * | Dismiss people to get food while first wine is poured
|  | * | Commence event when people return to their seats.
|  | * | Wrap up event before 9:00, to leave time for cleanup
After the event, clean/rinse/dry supplies (pourers, tongs, buckets, pitchers)
& return supplies to storage and return keys to the person borrowed from.
Submit a billing for reimbursement of expenses with receipts to the treasurer
either at the event or immediately following
Assign someone from the committee to attend the board meeting following the
event to report (usually the Thursday following the event)